## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Product Backlog
| Table 1 | Product Backlog
Sprint Backlog
| Table 1 | Sprint Backlog
Stand up Meeting
| Table 1 | Stand up Meeting
Retrospection
| Table 1 | Retrospection

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US1 | As a developer, I want to analyze the IVR system so that I can understand the call flow. | Must Have | IVR access | Backend Team | Completed
Sprint 2 | Sprint 2 | US2 | As a developer, I want to integrate Twilio with the backend so that calls can be handled programmatically | Must Have | Twilio setup | Backend Team | Completed
Sprint 3 | Sprint 3 | US3 | As a system, I want to support voice-based interaction so that users can speak instead of pressing buttons. | Should Have | Integration Layer | Backend Team | Completed
Sprint 4 | Sprint 4 | US4 | As a user, I want to check PNR status and train details so that I can get information easily. | Must Have | Backend APIs | Backend Team | Completed
Sprint 4 | Sprint 4 | US5 | As a DevOps engineer, I want to test and deploy the system so that it works properly in real-time. | Could Have | Full system integration | Both Teams | In progress
Note on F1: Sumeet Kumar Barua08: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US1 | T1 | Analyze IVR system and understand call flow | 2026-02-02 | 2026-02-10 | Backend1 | Analysis | Done | 6 | bar: Day 1 to Day 2
US1 | T2 | Identify requirements for conversational AI | 2026-02-11 | 2026-02-16 | Backend2 | Requirement | Done | 6 | bar: Day 3 to Day 4
US2 | T3 | Develop integration layer using FastAPI and Twilio | 2026-02-17 | 2026-03-02 | Backend3 | Integration | Done | 10 | bar: Day 2; Day 4; Day 6
US2 | T4 | Implement backend services for PNR and train data | 2026-02-25 | 2026-03-03 | Backend4 | Backend Development | Done | 8 | bar: Day 8; Day 10; Day 14
US3 | T5 | Develop conversational AI flow with speech input/output | 2026-03-06 | 2026-03-16 | Backend5 | AI Development | Done | 12 | bar: Day 4; Day 6; Day 9; Day 14
US4 | T6 | Test and deploy IVR system in real-time environment | 2026-03-17 | 2026-03-30 | Both Teams | Testing & Deployment | In progress | 12 | bar: Day 1; Day 4; Day 6; Day 8; Day 10
Note on D2: Sumeet Kumar Barua08: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Sumeet Kumar Barua08: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: Sumeet Kumar Barua08: This is the total task estimated in hours for all the user stories
Note on J3: Sumeet Kumar Barua08: Pending effort hours after completion of day 1 work
Note on K3: Sumeet Kumar Barua08: Pending effort hours after completion of day 2 work
Note on L3: Sumeet Kumar Barua08: Pending effort hours after completion of day 3 work
Note on M3: Sumeet Kumar Barua08: Pending effort hours after completion of day 4 work
Note on N3: Sumeet Kumar Barua08: Pending effort hours after completion of day 5 work
Note on O3: Sumeet Kumar Barua08: Pending effort hours after completion of day 6 work
Note on P3: Sumeet Kumar Barua08: Pending effort hours after completion of day 7 work
Note on Q3: Sumeet Kumar Barua08: Pending effort hours after completion of day 8 work
Note on R3: Sumeet Kumar Barua08: Pending effort hours after completion of day 9 work
Note on S3: Sumeet Kumar Barua08: Pending effort hours after completion of day 10 work
Note on T3: Sumeet Kumar Barua08: Pending effort hours after completion of day 11 work
Note on U3: Sumeet Kumar Barua08: Pending effort hours after completion of day 12 work
Note on V3: Sumeet Kumar Barua08: Pending effort hours after completion of day 13 work
Note on W3: Sumeet Kumar Barua08: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Difficulty understanding IVR call flow | Referred documentation and tested sample webhook
Sprint 1 | Day 4 | Confusion in mapping conversational flow | Broke flow into smaller steps and implemented logic
Sprint 2 | Day 2 | Twilio integration not working properly | Checked credentials and fixed API configuration
Sprint 2 | Day 6 | Speech input not captured correctly | Updated Gather settings and added speechTimeout
Sprint 3 | Day 6 | Voice input not recognizing numbers clearly | Added hints and improved speech handling
Sprint 4 | Day 2 | Delay in generating response from backend APIs | Optimized API calls and improved response formatting
Sprint 4 | Day 6 | Issues in deployment and webhook connection after hosting on Render | Updated webhook URL to deployed link and verified end-to-end flow
Sprint 4 | Day 10 | Performance inconsistency during multiple requests (In progress) | Conducting load testing and optimizing response handling

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-02-02 | 2026-02-16 | Backend Team | Understand IVR flow and Twilio basics clearly | Jumping into coding without full understanding | Learning through documentation and testing | Created basic IVR flow and tested webhook responses
2 | 2 | 2026-02-17 | 2026-03-02 | Backend Team | Test API responses during integration | Ignoring small errors in API responses | Debugging step-by-step during development | Fixed Twilio integration and backend data handling
3 | 3 | 2026-03-03 | 2026-03-16 | Backend Team | Improve speech recognition and intent handling | Using basic input handling without optimization | Enhancing conversational flow | Improved voice recognition and response accuracy
4 | 4 | 2026-03-17 | 2026-03-30 | Frontend + Backend | Test system along with frontend integration early | Waiting till the end for deployment testing | Regular testing and integration | Deployed IVR system and fixed integration issues