## Defect_tracker
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 2026-02-04 | Difficulty understanding existing IVR flow and system behavior | Sprint 1 | Backend Team | Functional | Analyzed IVR flow and documented system structure | 2026-02-06 | Closed | System understanding improved
2 | 2026-02-13 | Identified gaps between legacy IVR and conversational AI requirements | Sprint 1 | Backend Team | Analysis | Documented integration requirements and constraints | 2026-02-15 | Closed | Requirements finalized
3 | 2026-02-20 | Integration layer not properly connecting IVR with backend services | Sprint 2 | Backend Team | Integration | Developed and fixed API connections between modules | 2026-02-22 | Closed | Integration working
4 | 2026-02-28 | Data flow inconsistency between IVR and backend APIs | Sprint 2 | Backend Team | Integration | Improved data handling and response mapping | 2026-03-01 | Closed | Data flow stable
5 | 2026-03-08 | Conversational flow not aligning with IVR logic | Sprint 3 | Backend Team | Functional | Redesigned dialogue flow mapping with IVR system | 2026-03-10 | Closed | Flow-aligned
6 | 2026-03-12 | Voice input not properly interpreted for user queries | Sprint 3 | Backend Team | Functional | Enhanced speech handling and intent recognition | 2026-03-14 | Closed | Voice handling improved
7 | 2026-03-18 | Full system integration issues during testing phase | Sprint 4 | Backend Team | Integration | Fixed end-to-end flow and webhook configuration | 2026-03-19 | Closed | System integrated
8 | 2026-03-23 | System not handling edge cases during testing | Sprint 4 | Backend Team | Functional | Added fallback and error handling mechanisms | 2026-03-24 | Closed | Edge cases handled
9 | 2026-03-26 | Performance delay observed during multiple requests | Sprint 4 | Backend Team | Performance | Conducted load testing and optimized response time | 2026-03-27 | Closed | Performance improved
10 | 2026-03-29 | Minor issues in deployment and system response clarity | Sprint 4 | Backend Team | Deployment | Fixed deployment configuration and improved responses | 2026-03-30 | Closed | Deployment successful